## Sheet1
TASK | START DATE | DAYS TO COMPLETE
Team Formation | 2023-03-13 | 4
Project Approval | 2023-03-17 | 6
Implementation using Arduino Nano | 2023-03-23 | 5
Synopsis Submission | 2023-03-28 | 3
Schematic + report preparation | 2023-03-31 | 4
Coding | 2023-04-04 | 6
Testing and Debugging | 2023-04-10 | 3
PCB Fabrication | 2023-04-13 | 7
Testing and Debugging | 2023-04-20 | 3
Documentation | 2023-04-23 | 1
44998